Bluefly Agent Platform

Implementation Audit & Prioritized Next-Steps Plan

AgentSkills as a Service · Fleet Control Plane · OSSA Compliance

Prepared for: Thomas Scola, Founder & Principal Consultant

Bluefly.io | March 2026

Classification: Internal — Agentic Engineering Audience

# Table of Contents

# 1. Categorized Change Audit

This section audits all recent architectural changes, API contracts, agent lifecycle, execution model, and security posture against the canonical platform state defined in AGENTS.md, CLAUDE.md, and the AgentSkills as a Service architecture recommendation.

## 1.1 Architecture Changes

### 1.1.1 Package-First Consumption (2026-02-27)

Change: All 20 TypeScript platform services consumed via npm from GitLab registry, not git clones. Old NAS clones archived to _archive/services-agent-platform-git-clones/.

Impact: Eliminates clone drift between NAS/Oracle/Mac. Simplifies onboarding. Forces clean dependency boundaries.

Status: COMPLETE — enforced in CI; NAS clones removed.

### 1.1.2 Three-Tier OSSA Architecture

Change: Canonical three-tier split — Tier 1: platform-agents (YAML manifests only), Tier 2: common_npm (18 @bluefly/* TypeScript packages), Tier 3: gitlab-agent_ossa (Go).

Status: STABLE — 67 agents registered across 12 domains. CI validates manifest schema.

Gap: No automated drift detection between manifest declared capabilities and actual package exports. Proposed @bluefly/skill-registry would close this.

### 1.1.3 Separation of Duties Enforcement

Change: CI-enforced SoD via separation-of-duties-check from gitlab_components. compliance-engine PROJECT_BOUNDARIES and agent-mesh separation-of-duties.ts validate at runtime.

Status: ENFORCED — CI blocks cross-boundary imports.

Gap: alternative_services Phase 2 incomplete — DdevAddon entity, controllers, and forms remain in core module instead of alternative_ddev submodule. Requires migration to satisfy SoD split.

### 1.1.4 OSSA Four-Repo SoD

Change: Clear ownership split: openstandardagents (spec/CLI only), openstandardagents.org (marketing + thin YAML editor), openstandard-ui (the app: creator/save/pipelines), openstandard-generated-agents (artifact store only).

Status: DEFINED — boundaries documented but openstandard-ui overlap with .org editor not fully tested in CI.

## 1.2 API Contract Changes

### 1.2.1 Workflow-Engine Stable API

Three declared endpoints:

| Endpoint | Method | Status | Notes |
| --- | --- | --- | --- |
| POST /api/v1/flows/{flowId}/execute | Execute flow by ID | IMPLEMENTED | Production-ready |
| POST /api/v1/flows/execute-by-name | Execute by name | NOT IMPLEMENTED | Blocks Drupal dynamic dispatch |
| POST /api/v1/trigger | Drupal payload trigger | NOT IMPLEMENTED | Blocks ECA → platform flow integration |

Impact: 2 of 3 stable API endpoints missing. Drupal integration cannot proceed until execute-by-name and /trigger are available.

### 1.2.2 Drupal Orchestration Module

Status: ServicesProviderInterface with 8 implementations across submodules. Endpoints: GET /orchestration/services, POST /orchestration/service/execute, webhook register/unregister/poll.

Gap: Webhook endpoints depend on workflow-engine /trigger which does not exist yet. orchestration module release was recent — no E2E tests covering full Drupal → TypeScript → callback chain.

### 1.2.3 AgentSkills.io Format Compatibility

Change: Architecture recommendation proposes Format Normalizer to bridge OSSA manifests ↔ AgentSkills.io SKILL.md format.

Status: NOT BUILT — no code exists. The format gap between OSSA YAML manifests and AgentSkills.io frontmatter+markdown is unbridged.

## 1.3 Agent Lifecycle Changes

### 1.3.1 Fleet 7-Step Pipeline

DESCRIBE→GENERATE→CLASSIFY→GATE→ROLLOUT→VERIFY→PULSE

Status: Steps 1-3 (describe, generate, classify) functional via BuildKit CLI. Steps 4-7 require Cedar policy gates and fleet deploy infrastructure.

Gap: Cedar policy gates not enforced at runtime — tier_3 (deploy) and tier_4 (fleet-wide) gates are defined but the enforcement middleware in agent-router has no tests. ROLLOUT step depends on kagent deploy endpoint which is not implemented.

### 1.3.2 Drupal Agent Marketplace

Status: POC functional — Drupal backend (ai_agents_marketplace, recipe_agent_marketplace), Node frontend (NODE-AgentMarketplace).

- kagent deploy endpoint: NOT IMPLEMENTED — blocks one-click agent deployment from marketplace UI.

- User auth E2E: NOT TESTED — per-user GitLab project flow has no integration tests.

- Wizard E2E: No end-to-end flow covering full wizard → save → deploy → verify chain.

### 1.3.3 Skill Lifecycle (AgentSkills Integration)

Decision: AgentSkills integration module placed in alternative_services/alternative_skills (per AGENTS.md line 384).

Status: NOT BUILT — module directory does not exist. @bluefly/skill-registry npm package also not created. No CRUD operations for skill discovery, install, validate, publish.

## 1.4 Execution Model Changes

### 1.4.1 Agentic Flows Contract

Architecture: Drupal (ECA, FlowDrop, orchestration) ↔ TypeScript (agentic-flows definitions, workflow-engine execution) via HTTP/Tool.

Status: TypeScript side: agentic-flows has flow definitions, workflow-engine has execution runtime with 1 of 3 endpoints. Drupal side: ECA and FlowDrop functional, orchestration ServicesProviderInterface done.

Gap: 'Invoke platform flow' ECA action — the Drupal ECA action that calls workflow-engine /trigger does not exist. This is the critical bridge action that enables Drupal-initiated agentic workflows.

### 1.4.2 OSSA Export → n8n/Zapier Pipeline

7-step flow: manifest → parse → orchestration adapter → tool plugin → webhook → n8n node → external automation.

Status: Steps 1-4 documented and partially implemented (orchestration ServicesProviderInterface). Steps 5-7 (webhook delivery, n8n custom node, Zapier integration) require workflow-engine /trigger endpoint.

## 1.5 Security Changes

### 1.5.1 1Password Token Management

Policy: Three sinks only — BuildKit/NAS (.env.local), Oracle (env vars), Mac dev (env). No master token in files. Automation uses GitLab service-account tokens.

Status: ENFORCED — buildkit gitlab token pat-self-rotate automates PAT rotation.

Gap: No automated alerting when tokens approach expiry. n8n admin and MCP API tokens (1Password vault) lack rotation schedule.

### 1.5.2 Cedar Policy Gates

Status: Policy definitions exist for tier_1 through tier_4. compliance-engine validates.

Gap: No integration tests covering Cedar deny scenarios. Policy update workflow (who can modify Cedar policies, how they deploy) is undocumented.

### 1.5.3 Agent Role Separation

| Agent | Role | Tier | Conflicts |
| --- | --- | --- | --- |
| vulnerability-scanner | Analyzer | tier_1_read | Executor, Approver |
| merge-request-reviewer | Reviewer | tier_2_write | Executor, Approver |
| pipeline-remediation | Executor | tier_3_full | Reviewer, Approver |
| release-coordinator | Orchestrator | tier_2_write | Executor (direct) |

Status: ENFORCED — agent-mesh separation-of-duties.ts validates conflict matrix at runtime.

# 2. Gap Analysis

Each gap is mapped to the specific project, environment, and requirement it blocks.

| # | Gap | Blocks | Project/Env | Severity |
| --- | --- | --- | --- | --- |
| G1 | workflow-engine execute-by-name endpoint | Drupal dynamic dispatch, orchestration by name | workflow-engine / Oracle | CRITICAL |
| G2 | workflow-engine /trigger endpoint | ECA → platform flows, n8n integration, OSSA export steps 5-7 | workflow-engine / Oracle | CRITICAL |
| G3 | ECA action 'Invoke platform flow' | Drupal-initiated agentic workflows | ai_agents_ossa / Drupal | CRITICAL |
| G4 | @bluefly/skill-registry package | Skill CRUD, GKG indexing, AgentSkills format bridge | common_npm / npm | HIGH |
| G5 | Format Normalizer (OSSA ↔ AgentSkills) | Publishing skills to AgentSkills.io, external discovery | new component / npm | HIGH |
| G6 | kagent deploy endpoint | One-click agent deploy from marketplace | NODE-AgentMarketplace / Oracle | HIGH |
| G7 | alternative_services Phase 2 split | SoD compliance for DDEV addon code | all_drupal_custom / Drupal | MEDIUM |
| G8 | Cedar policy integration tests | Confidence in tier_3/tier_4 gate enforcement | compliance-engine / CI | MEDIUM |
| G9 | Wizard E2E test flow | Marketplace wizard reliability | openstandard-ui / CI | MEDIUM |
| G10 | User auth E2E (per-user GitLab project) | Marketplace user onboarding | NODE-AgentMarketplace / CI | MEDIUM |
| G11 | Composer migration (remaining projects) | Clean dependency resolution for Drupal projects | all_drupal_custom / Packagist | MEDIUM |
| G12 | Fleet Skill Deploy component | Fleet-wide skill rollout via fleet-ops pipeline | new component / Oracle | MEDIUM |
| G13 | Token expiry alerting | Proactive token rotation before failures | agent-buildkit / n8n | LOW |
| G14 | Security Scanner for skills | Skill supply-chain validation before fleet deploy | new component / CI | LOW |
| G15 | Manifest ↔ package export drift detection | Catching mismatches between declared and actual capabilities | CI / gitlab_components | LOW |

## 2.1 Dependency Graph

Critical path dependencies determine sequencing:

- G2 → G3 → G5: /trigger endpoint enables ECA action, which enables orchestration export pipeline, which is needed for AgentSkills publishing.

- G1 → G4: execute-by-name enables skill-registry dynamic invocation.

- G4 → G5 → G12: skill-registry enables format normalizer, which enables fleet skill deploy.

- G6 → G10 → G9: kagent deploy enables user auth flow, which enables full wizard E2E.

## 2.2 Environment Impact Matrix

| Environment | Blocked Gaps | Impact |
| --- | --- | --- |
| Oracle (production) | G1, G2, G6, G12 | No new workflow endpoints, no marketplace deploy, no fleet skill rollout |
| Drupal (DDEV/Acquia) | G3, G7, G11 | No ECA bridge action, SoD non-compliant, incomplete Composer migration |
| CI/CD (GitLab) | G8, G9, G10, G14, G15 | Missing integration tests, no E2E wizard, no security scanning |
| npm (GitLab registry) | G4, G5 | No skill-registry or format normalizer packages published |

# 3. Prioritized Remediation & Enhancement Plan

Sequenced into four phases with explicit dependencies. Each work item references the gap ID from Section 2.

## 3.1 Phase 1 — Critical Path (Weeks 1-2)

Goal: Unblock the Drupal ↔ TypeScript integration bridge and marketplace deploy.

### 3.1.1 Implement workflow-engine execute-by-name [G1]

- Project: common_npm/workflow-engine

- Action: Add POST /api/v1/flows/execute-by-name endpoint. Accept { name, version?, input } body. Resolve flow by name from agentic-flows registry. Return execution result.

- Tests: Unit tests for name resolution, integration test with agentic-flows mock, error handling for missing/ambiguous names.

- Deploy: Oracle via CI on merge to release/v0.1.x.

### 3.1.2 Implement workflow-engine /trigger [G2]

- Project: common_npm/workflow-engine

- Action: Add POST /api/v1/trigger endpoint. Accept Drupal-shaped payload (entity_type, bundle, action, data). Map to flow execution via name convention or explicit mapping table.

- Tests: Integration test with Drupal orchestration webhook payload. Callback verification to Drupal webhook endpoint.

- Dependency: Implements after 3.1.1 (shares flow resolution logic).

### 3.1.3 Build ECA action 'Invoke platform flow' [G3]

- Project: all_drupal_custom/ai_agents_ossa

- Action: Create ECA action plugin that calls workflow-engine /trigger. Configure via ECA UI: flow name, payload mapping, callback URL.

- Tests: PHPUnit for action plugin. DDEV integration test: ECA event → action → HTTP call → verify trigger received.

- Dependency: Requires G2 deployed on Oracle.

### 3.1.4 Implement kagent deploy endpoint [G6]

- Project: NODE-AgentMarketplace

- Action: Add POST /api/agents/{agentId}/deploy endpoint. Trigger kagent-based deployment pipeline. Return deployment status with polling URL.

- Tests: Mock kagent integration, verify pipeline trigger, test rollback on failure.

## 3.2 Phase 2 — Skill Infrastructure (Weeks 3-4)

Goal: Build the skill lifecycle layer and close the AgentSkills format gap.

### 3.2.1 Create @bluefly/skill-registry [G4]

- Project: common_npm (new package)

- Action: Full CRUD for skill manifests. GKG integration for semantic indexing. Skill validation (schema check, dependency resolution, security scan stub). Expose via MCP tool for agent-protocol.

- Interface: SkillRegistry { create, read, update, delete, search, validate, publish }. Zod schemas for all inputs.

- Tests: Unit tests for CRUD, integration test with GKG mock, MCP tool integration test.

### 3.2.2 Build Format Normalizer [G5]

- Project: common_npm (new package or module in skill-registry)

- Action: Bidirectional conversion: OSSA YAML manifest ↔ AgentSkills.io SKILL.md (frontmatter + markdown). Handle capability mapping, input/output schema translation, metadata preservation.

- Tests: Round-trip tests: OSSA → AgentSkills → OSSA with diff verification. Edge cases: multi-tool agents, nested schemas.

- Dependency: Requires G4 for registry integration.

### 3.2.3 Complete alternative_services Phase 2 [G7]

- Project: all_drupal_custom/alternative_services

- Action: Migrate DdevAddon entity type, controllers, forms, and routes from core module to alternative_ddev submodule. Update service references and dependency injection.

- Tests: Verify DDEV addon CRUD after migration. Run existing test suite to catch regressions.

### 3.2.4 Cedar policy integration tests [G8]

- Project: common_npm/compliance-engine

- Action: Write integration tests covering: tier_3 deploy gate (approve/deny scenarios), tier_4 fleet-wide gate, policy update rejection for unauthorized agents, conflict matrix enforcement.

- Tests: Minimum 8 test cases covering all 4 tiers and 2 deny scenarios per tier.

## 3.3 Phase 3 — Marketplace & Fleet (Weeks 5-6)

Goal: E2E marketplace flows and fleet skill deployment.

### 3.3.1 User auth E2E tests [G10]

- Project: NODE-AgentMarketplace

- Action: Integration test: user signup → GitLab project creation → agent fork → deploy → verify running. Cover OAuth flow, project permissions, cleanup on failure.

### 3.3.2 Wizard E2E test flow [G9]

- Project: openstandard-ui

- Action: Playwright E2E: open wizard → configure agent → save manifest → trigger pipeline → verify artifact in openstandard-generated-agents. Test abort/resume.

- Dependency: Requires G6 (deploy endpoint) and G10 (user auth) from Phase 1-2.

### 3.3.3 Build Fleet Skill Deploy [G12]

- Project: new component (fleet-skill-deploy in common_npm or agent-buildkit command)

- Action: Integrate with fleet-ops 7-step pipeline. Steps: validate skill (schema + security) → classify target fleet → Cedar gate check → staged rollout (canary → 10% → 50% → 100%) → verify health → GKG pulse update.

- Dependency: Requires G4 (skill-registry) and G8 (Cedar tests).

### 3.3.4 Composer migration completion [G11]

- Project: all_drupal_custom (multiple modules)

- Action: Publish remaining custom modules to GitLab group Composer registry. Update TESTING_DEMOS and WORKING_DEMOs composer.json to pull from registry. Verify composer update succeeds for all 5 OSSA WORKING_DEMOs.

## 3.4 Phase 4 — External & Hardening (Weeks 7+)

Goal: External publishing, security scanning, observability.

### 3.4.1 Security Scanner for skills [G14]

- Action: Supply-chain validation: dependency audit, code pattern scanning (no eval, no network calls without declaration), license compliance check. Integrate into fleet-ops GATE step.

### 3.4.2 Manifest ↔ export drift detection [G15]

- Action: CI job in gitlab_components that compares manifest declared capabilities against actual package.json exports. Fails MR if mismatch detected.

### 3.4.3 Token expiry alerting [G13]

- Action: n8n workflow: daily check of PAT expiry dates via GitLab API. Alert via webhook if any token expires within 7 days. Include n8n admin and MCP API tokens from 1Password vault.

### 3.4.4 AgentSkills.io publishing pipeline

- Action: Extend skill-registry with publish-to-external command. Format normalize → validate → push to AgentSkills.io registry API. Include CI job for automated publishing on tag.

### 3.4.5 Bloom/Research sync integration

- Action: Connect Zotero/Obsidian NAS research library with GKG for semantic skill discovery. Map research papers to relevant skills via @bluefly/agent-brain.

# 4. Risks, Blockers & Required Design Decisions

## 4.1 Blockers (Must Resolve Before Phase Start)

| Blocker | Blocks | Resolution | Owner |
| --- | --- | --- | --- |
| workflow-engine /trigger contract not finalized | Phase 1 items G2, G3 | Finalize payload schema: { entity_type, bundle, action, data, callback_url }. Document in OpenAPI spec. | Lead Architect |
| Cedar policy update workflow undefined | Phase 2 item G8 | Define who can author/review/deploy Cedar policies. Document in wiki architecture/. | Security Lead |
| AgentSkills.io registry API access | Phase 4 publishing | Obtain API credentials and review ToS. Evaluate rate limits and publishing requirements. | Platform Lead |
| kagent deployment model undocumented | Phase 1 item G6 | Document kagent deploy → K8s flow: namespace isolation, resource limits, health check requirements. | Infrastructure Lead |

## 4.2 Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Drupal orchestration module API instability (recently released) | MEDIUM | HIGH | Pin orchestration version in composer.lock. Integration tests run nightly against latest. Feature-flag ECA action behind config toggle. |
| AgentSkills.io spec changes during integration | MEDIUM | MEDIUM | Format normalizer uses adapter pattern — isolate AgentSkills-specific logic in single module. Monitor spec repo for breaking changes. |
| Cedar gate enforcement gaps in production | LOW | CRITICAL | Phase 2 integration tests (G8) are prerequisite before any tier_3+ deployment. Add runtime Cedar deny logging to Grafana dashboard. |
| Composer migration breaks existing Drupal sites | MEDIUM | HIGH | Run composer update --dry-run in all 5 WORKING_DEMOs before publishing. Keep git clone fallback in composer.json repositories for 2-week transition. |
| Fleet skill rollout causes agent regression | LOW | HIGH | Canary deployment in fleet-skill-deploy (10% → verify → expand). Automatic rollback trigger on health check failure. |
| Token rotation gap causes CI/CD outage | MEDIUM | MEDIUM | Phase 4 alerting (G13) provides 7-day warning. Document manual rotation runbook in wiki. |

## 4.3 Required Design Decisions

- Skill-registry storage backend: GKG-native (Qdrant vectors + PostgreSQL metadata) vs. GitLab Package Registry metadata vs. hybrid. Recommendation: hybrid — GKG for semantic search, GitLab for versioned artifacts.

- Format normalizer scope: Standalone @bluefly/format-normalizer package vs. module within @bluefly/skill-registry. Recommendation: module within skill-registry (fewer packages, shared types).

- ECA action configuration model: Hard-coded flow names vs. dynamic discovery via workflow-engine /flows endpoint. Recommendation: dynamic discovery with cached manifest for offline fallback.

- Fleet skill deploy rollout strategy: Percentage-based (canary) vs. ring-based (dev → staging → prod fleet). Recommendation: ring-based for multi-environment, percentage within each ring.

- AgentSkills.io publishing trigger: Manual (BuildKit command) vs. automated (CI on tag to main). Recommendation: automated with manual gate (require explicit label 'publish-external' on MR).

- Marketplace user isolation model: Per-user GitLab project (current design) vs. per-user namespace in shared project. Recommendation: keep per-user project for strongest isolation; add cleanup automation for abandoned projects.

# 5. CI/CD, Testing & Documentation Work Items

## 5.1 CI/CD Pipeline Work Items

| Item | Project | Phase | Description |
| --- | --- | --- | --- |
| Add workflow-engine integration test stage | gitlab_components | 1 | New CI template: spin up workflow-engine, run Drupal integration tests, teardown. Reusable across projects. |
| Manifest drift detection job | gitlab_components | 4 | Compare OSSA manifest capabilities against package.json exports. Block MR on mismatch. |
| Skill security scan job | gitlab_components | 4 | Scan skill code for unsafe patterns (eval, dynamic require, undeclared network). Run on skill MRs. |
| Composer publish job | all_drupal_custom CI | 3 | Automate composer package publish to GitLab group registry on tag. Include version validation. |
| E2E marketplace pipeline | openstandard-ui CI | 3 | Playwright E2E running against staging marketplace. Triggered on MR and nightly. |
| Cedar policy deploy pipeline | compliance-engine CI | 2 | Lint → test → deploy Cedar policies. Require two approvals for production policy changes. |
| Token rotation check | n8n workflow | 4 | Daily: GitLab API check for expiring PATs. Alert channel: webhook to platform monitoring. |
| SoD validation in MR pipeline | gitlab_components | 1 | Extend separation-of-duties-check to validate Drupal module boundaries (not just npm packages). |

## 5.2 Testing Requirements

### 5.2.1 Unit Tests (Per-Package)

| Package | Required Tests | Current Coverage | Target |
| --- | --- | --- | --- |
| workflow-engine | execute-by-name resolution, /trigger payload mapping, callback delivery | ~60% (execute-by-id only) | ≥85% |
| skill-registry (new) | CRUD operations, GKG integration, validation, MCP tool | 0% (new) | ≥90% |
| compliance-engine | Cedar gate evaluation for all 4 tiers, deny scenarios, policy loading | ~50% | ≥85% |
| format-normalizer (new) | OSSA→AgentSkills, AgentSkills→OSSA, round-trip, edge cases | 0% (new) | ≥90% |
| agent-router | Cedar middleware enforcement, tier routing, conflict detection | ~70% | ≥85% |

### 5.2.2 Integration Tests

- Drupal → workflow-engine E2E: ECA event fires → 'Invoke platform flow' action → /trigger call → flow executes → callback to Drupal → verify entity updated.

- Marketplace deploy E2E: POST /api/agents/{id}/deploy → kagent pipeline → K8s pod running → health check passing → marketplace status updated.

- Skill lifecycle E2E: Create skill via registry → validate → format normalize → publish to AgentSkills.io staging → verify listing.

- Fleet rollout E2E: Skill validated → Cedar gate approved → canary deploy → health verify → expand → GKG pulse updated.

### 5.2.3 Performance Tests

- workflow-engine /trigger throughput: Target ≥100 concurrent triggers without degradation. Measure p99 latency.

- skill-registry search latency: GKG semantic search returns in <200ms for 90th percentile with 1000+ indexed skills.

- Fleet rollout timing: Full fleet (67 agents) skill deploy completes within 15 minutes including all verification steps.

## 5.3 Documentation Work Items

| Document | Location | Phase | Content |
| --- | --- | --- | --- |
| workflow-engine /trigger OpenAPI spec | api-schema-registry | 1 | Full OpenAPI 3.1 spec for /trigger endpoint including Drupal payload schema, callback contract, error codes |
| ECA action 'Invoke platform flow' guide | GitLab Wiki (ai_agents_ossa) | 1 | Configuration guide: how to set up ECA rule with platform flow action, payload mapping, troubleshooting |
| skill-registry API reference | GitLab Wiki (technical-docs) | 2 | CRUD endpoints, MCP tool usage, GKG integration, format normalizer usage |
| Cedar policy authoring guide | GitLab Wiki (technical-docs/architecture) | 2 | How to write, test, review, and deploy Cedar policies for agent tiers |
| AgentSkills.io publishing runbook | GitLab Wiki (technical-docs) | 4 | Step-by-step: format normalize, validate, publish. CI automation. Monitoring published skills. |
| Fleet skill deploy operations guide | GitLab Wiki (technical-docs) | 3 | Rollout strategy, canary config, rollback procedures, health check requirements, GKG pulse interpretation |
| Marketplace admin guide (Drupal backend) | GitLab Wiki (ai_agents_marketplace) | 3 | Agent lifecycle management, user project provisioning, deploy status monitoring, cleanup procedures |
| Composer migration runbook update | AGENTS.md | 3 | Update 6-step runbook with remaining project specifics, verification steps for all 5 WORKING_DEMOs |

## 5.4 Phase Execution Summary

| Phase | Weeks | Work Items | Gaps Closed | Key Deliverable |
| --- | --- | --- | --- | --- |
| 1 — Critical Path | 1-2 | 4 implementation + 2 CI + 2 docs | G1, G2, G3, G6 | Drupal ↔ TypeScript bridge operational |
| 2 — Skill Infrastructure | 3-4 | 4 implementation + 1 CI + 2 docs | G4, G5, G7, G8 | Skill lifecycle and Cedar gates validated |
| 3 — Marketplace & Fleet | 5-6 | 4 implementation + 2 CI + 2 docs | G9, G10, G11, G12 | Full E2E marketplace and fleet skill deploy |
| 4 — External & Hardening | 7+ | 5 implementation + 2 CI + 2 docs | G13, G14, G15 + publishing | External AgentSkills.io integration live |